## Sheet1
Project plan

Company Name:	Opulence		Project Manager	Nikhil Parab
Project Name:	Opulence Antivirus Software Development Project		Project location	Pune, Maharashtra
E-Mail:	123 antivirus@gmail.com		Start date	01/01/20
Phone :	9587126154		End Date	28/05/20
Activities/Tasks

Sr.No.	Activity Name	Start Date	End Date	Duration(in days)	Budget
1	Backend working	01/01/20	01/02/23	45 days	1000$
2	Database Integration	01/01/20	05/03/23	30 days	1000$
3	Frontend Working	01/02/20	01/08/23	50 days	1200$
4	Launch and Marketing	01/06/20	01/11/23	20 days	2000$
5	Software testing	01/06/20	01/01/24	31 days	2000$
6	Documentation	25/05/20	02/05/20	30 days	50$

## ES
Project Charter

Project Name:	Coursera Educational website			Project Manager	Anuj Dagade
Project Start Date:	27/02/24	Project End Date:	02/05/24	Project Sponsor	Rajesh Verma
Business Need

To Make it easier for students to learn from home

Project Scope			Deliverables
Students can purchase courses. Take notes , Rent courses. 1. Quick access from anytime, anywhere. Since digital courses require only a laptop, smartphone or tablet with an internet connection, students can easily learn from anywhere at convenient times. 2. Course materials are accessible easily 3. students can access a variety of course offerings and gain diverse perspectives.

Risks
Project may go outside estimed budget. Changing requirements can extend the deadline of the project Change in leadership can affect project progress

Financials
Budget			5 Lakhs
Milestones
Milestone		Target Completion Date		Actual Date
Front End Development		18/03/24

Back End Development		29/03/24

Project Team			Approval/Review Committee

Project Manager		Anuj Dagade	Sponsor			Rajesh Verma
Project Sponsor		Rajesh Verma	Business Division Head			Kavya Nair
Project Members		Anuj Dagade / Rohan Dube / Kumar Abhijit	Business Unit Head			Surya Metha
			Finance Manager			Aisha Rane

## Sheet3
Project Schedule

Task		Duration
		(Weeks 1-2)
Initiation Phase		Define project scope, objectives, and deliverables.

		(Weeks 1-2)
Planning Phase		Create a risk management plan and mitigation strategies.

		(Weeks 2-3 )
Design and Architecture		Develop user interface prototypes.

		(Weeks 17-20)
Testing and Quality Assurance		Perform performance testing and optimize software for efficiency.

		(Weeks 29-30):
Documentation		review and update documentation based on final software features.

		(Weeks 31-32)
Launch and Marketing		Implement marketing strategies to promote the antivirus software. / Monitor initial user adoption and feedback.