## Sheet1
Project Charter

Project Name	E-commerce Website
Project Sponsor	AB Sponsor	Project Manager	Rohit Gadkari
Date of Project Approval	1st Jan 2024	Last Revision Date	2nd Jan 2024
Project Start	1st Jan 2024	Project deadline	1st April 2024
Project Description	Making E-Commerce website for the Company
Scope	This project will have features like COD,UPI support, refund within the day. E-commerce website of the company will enable it to enter the global market for serving the customers of various different countries. This will increase the sales of the products and will help the company in growing its market share
Business Case	To increase the sales by 40% by making it easier for customers to buy goods
Constraints	Time	4 months
	Budget	20 lakhs
	Quality	Prioritize time & budget over quality

Benefits
	KPI	Baseline	Goal
	Orders per day	120	200
	Unsolved queries per day	15	5
	customer satisfaction	30	80
		Project Team	Sales Rep
Steering Committee	CEO		5 developers
	Finance Director		1 Tester
	Sales Director

Risks	Exceeding the budget with vast margin.