## Sheet1
Project plan

Company Name:	Opulence		Project Manager	Nikhil Parab
Project Name:	Opulence Antivirus Software Development Project		Project location	Pune, Maharashtra
E-Mail:	123 antivirus@gmail.com		Start date	01/01/20
Phone :	9587126154		End Date	28/05/20
Activities/Tasks

Sr.No.	Activity Name	Start Date	End Date	Duration(in days)	Budget
1	Backend working	01/01/20	01/02/23	45 days	1000$
2	Database Integration	01/01/20	05/03/23	30 days	1000$
3	Frontend Working	01/02/20	01/08/23	50 days	1200$
4	Launch and Marketing	01/06/20	01/11/23	20 days	2000$
5	Software testing	01/06/20	01/01/24	31 days	2000$
6	Documentation	25/05/20	02/05/20	30 days	50$

## Sheet2
Project Charter

Project Name:	Opulence Antivirus Software Development Project			Project Manager	Nikhil Parab
Project Start Date:	01/01/20	Project End Date:	28/05/20	Project Sponsor	Rajesh Verma
Business Need

Develop a cutting-edge antivirus software solution to safeguard user systems, data, and privacy against evolving cyber threats, ensuring a secure computing environment for our customers and establishing our brand as a trusted leader in cybersecurity.

Project Scope			Deliverables
This project work focuses on developing an software for detecting and deleting the system threat only.			Fully functional antivirus software . A user-friendly antivirus software with accompanying documentation and quality assurance reports to ensure robust protection against cyber threats.

Risks and Issues			Assumptions/Dependencies
Antivirus software Project risk and issues. Compatibility issues may arise when integrating the Antivirus software with various operating systems and third-party applications. The discovery of bugs or glitches in the software during testing or post-launch.			Stable and well-documented APIs from third-party vendors for integration with threat intelligence and other services. Customer will actively participate in beta testing and provide valuable feedback. Timely availability of necessary hardware and software components for development and testing.

Financials
Budget to complete this Project is $7250
Milestones and Schedule
Milestone		Target Completion Date		Actual Date
1. Build 1.0 Beta Version of opulence Antivirus software		03/03/20		28/03/20

1. Build 2.0 Version of opulence Antivirus software adding new features of Beta		29/04/20		04/04/20

Project Team			Approval/Review Committee

Project Manager		Nikhil Parab	Sponsor			Rajesh Verma
Project Sponsor		Rajesh Verma	Business Division Head			Kavya Nair
Project Members		Arjun Patel ,Priya Singh,Rahul Kumar	Business Unit Head			Surya Metha
			Finance Manager			Aisha Rane

## Sheet3
Project Schedule

Task		Duration
		(Weeks 1-2)
Initiation Phase		Define project scope, objectives, and deliverables.

		(Weeks 1-2)
Planning Phase		Create a risk management plan and mitigation strategies.

		(Weeks 2-3 )
Design and Architecture		Develop user interface prototypes.

		(Weeks 17-20)
Testing and Quality Assurance		Perform performance testing and optimize software for efficiency.

		(Weeks 29-30):
Documentation		review and update documentation based on final software features.

		(Weeks 31-32)
Launch and Marketing		Implement marketing strategies to promote the antivirus software. / Monitor initial user adoption and feedback.