## Sheet1
		PROJECT CHARTER

Project Title	Pixel Market E commerce website				Project Manager	Nikhil Parab
Project Start Date : May 21, 2024				Project End Date : August 15, 2024			Project Sponsor : Aditya Wani
		BUSINESS NEED

Design an appealing website that reflects your brand and is optimized for mobile users. Prioritize secure payment gateways and transparent shipping strategies to build customer trust.

PROJECT SCOPE			The project includes defining business goals, conducting market research, selecting a user-friendly platform, designing an appealing website, ensuring secure payment methods, optimizing logistics, implementing effective marketing strategies, and adhering to legal requirements.

RISK AND ISSUES			potential risks and issues may arise in various areas. Supply chain disruptions, market competition, and technological challenges pose inherent risks to the e-commerce industry. Issues related to website functionality, security vulnerabilities, and potential data breaches need careful consideration. Furthermore, changes in government regulations and economic conditions can impact operations.

ASSUMPTIONS/DEPENDENCIES			Assumptions include anticipating stable market conditions, consistent supplier performance, and a steady demand for e-commerce services. Dependencies revolve around partnerships with reliable logistics and payment service providers, the availability of skilled IT professionals for ongoing platform development, and the effectiveness of marketing strategies to drive customer engagement.

DELIVERABLES			These include a fully functional and user-friendly website equipped with secure payment gateways and streamlined navigation. Deliverables also involve an integrated logistics system for efficient order fulfillment, ensuring timely and reliable product deliveries to customers.

		FINANCIALS

The cost of building an e-commerce website like Pixel-Market can range is $25,000

MILESTONES		Status:				Due:	Deadline:
		1. Build 1.0 Version of Pixel Market Website				21/06/24	25/06/24

		2. Build 2.0 Version of Pixel Market Website Adding new features after Beta – Testing				05/07/24	05/08/24

PROJECT TEAM					APPROVAL/REVIEW COMMITTEE

Project Manager		Nikhil Parab			Sponsor		Aditya Wani

Project Sponsor		Aditya Wani			Business Division Head		Kavya Nair

Project Member		Arjun Patel Priya Singh / Rahul Kumar AnanyaReddy / Rohit Desai			Business Unit Head		Surya Mehta
					Finance Manager		Aisha Rane

## Sheet2
Project Plan Template

Basic Information
Company Name: Pixel 1				Project Name: Pixel Market

Address: Pixel 1 Corporation Pvt. Ltd. / 123 Main Street / City - 560001 / State, India				Project Manager: Nikhil Parab
				Project Address: Pixel 1 Corparation Pvt. Ltd. 123 Main Street City – 560001 State, India

Phone: 5261478563
Email: Pixel 1 Global 123@gmail.com
Contact Name: Nikhil Parab		Contact Name		Project Deliverable: August 18,2024
Activities/Tasks

Sr.No.	Activity Name	Start Date	End Date	Duration(in days)	Budget	Remarks
1	Product Listing	01/01/24	01/02/24	31 days	80k
2	Order System	05/01/24	05/03/24	60 days	81k
3	Payment System	01/03/24	01/08/24	180 days	82k
4	Shipping	01/08/24	01/11/24	122 days	3k
5	Feedback	01/12/24	01/01/24	31 days	8k