## Sheet3
Project plan

2129, kapataru appts, new modikhana / Camp. / Pune, Maharashtra,India / 411001			Project Manager	Poonam Indalkar
			Project location	Pune
			Start date	01/01/23
			End Date	01/01/24
Activities/Tasks

Sr.No.	Activity Name	Start Date	End Date	Duration(in days)	Budget
1	Product Listing	01/01/23	01/02/23	31 days	80k
2	Order System	05/01/23	05/03/23	60 days	81k
3	Payment	01/03/23	01/08/23	180 days	82k
4	Shipping	01/08/23	01/11/23	122 days	83k
5	Feedback	01/12/23	01/01/24	31 days	84k