## Project Schedule
Project Schedule

	ASSIGNED TO:	MONDAY	TUESDAY	WEDNESDAY	THURSDAY	FRIDAY
Week 1	Anuj	Create model of DB	Select DB hosting service	Write API for DB	Test DB	Deploy DB
	Rohan	Write home page	Write About Us page	Wireframe home page	Wireframe About Us page	Wireframe Services page
	Ayush	configure NGINX server	Create Registration module	Test Registration module	Do code review of registration module	Write documentation for Registration module
	ASSIGNED TO:	MONDAY	TUESDAY	WEDNESDAY	THURSDAY	FRIDAY
Week 2	Anuj	Create Login module	Work on login module	Test Login module	Do code review of Login module	Write documentation for Login module
	Rohan	Select CDN	Work on content delivery system	Work on content delivery system	Work on content delivery system	Perform Test on CDN
	Ayush	Select Load Balancer	Configure Load Balancer	Configure Load Balancer	Test Load Balancer	Write documentation for Load Balancer